## Summary
LPG Smart Fleet Platform - Project Plan
Total estimate | 35 sessions (~6.5 calendar weeks at 5 sessions/week, includes 3 buffer days)
Definition of 1 day | 1 focused Claude session, ~4-6 hours
Phase totals
Phase | Name | Sessions | Start Day | End Day
1 | Foundation | 3 | 1 | 3
2 | Auth & Users | 2 | 4 | 5
3 | Geographic & Inventory Core | 3 | 6 | 8
4 | Orders & Dispatch | 3 | 9 | 11
5 | Payments, Returns, Notifications | 2 | 12 | 13
6 | Third-party Integrations | 4 | 14 | 17
7 | Mobile - Customer | 3 | 18 | 20
8 | Mobile - Distributor | 2 | 21 | 22
9 | Mobile - Driver | 2 | 23 | 24
10 | Backend Testing | 3 | 25 | 27
11 | Maps & Routing | 1 | 28 | 28
12 | Production Hardening | 2 | 29 | 30
13 | Deployment | 2 | 31 | 32
14 | Buffer | 3 | 33 | 35
| TOTAL | 35
Current progress
Item | Status
Repo initialized, branches main + claude/general-session-GxQxC exist | Done
Project requirements understood (Project_Overview.docx parsed) | Done
Local tooling available (Node 22, npm 10, Docker 29, psql 16) | Done
Plan written (WBS + Excel) | Done
Any code written | Not started (0%)
Estimating assumptions
Assumption | Value
1 "day" | 1 focused Claude session, ~4-6 hours of coding
Third-party APIs | Real wiring is in the plan (Twilio/Africa's Talking, Firebase FCM, JazzCash, Easypaisa, Google Maps)
Mobile scope | All 3 roles in v1: Customer, Distributor, Driver
Deployment target | Single VPS (DigitalOcean / Contabo / Hetzner) with docker-compose + nginx + Let's Encrypt
Cadence | 5 sessions per week -> ~6 calendar weeks total
Reviewer in the loop | User reviews each milestone before next begins; small follow-up fixes folded into the next day's buffer

## WBS
Phase | Phase Name | Task ID | Task Name | Sessions (days) | Start Day | End Day | Dependencies | Deliverables | Verification | Status
1 | Foundation | 1.1 | Bootstrap monorepo + infrastructure | 1 | 1 | 1 | - | Root package.json (npm workspaces), turbo.json, .gitignore, .env.example, tsconfig.base.json; infrastructure/docker-compose.yml (Postgres+PostGIS, Redis, MinIO); packages/shared-types and packages/shared-utils (haversine.ts); docs/ folder skeleton. | docker compose up -d brings postgres, redis, minio healthy; psql connects; redis-cli ping -> PONG; npm install resolves workspaces. | Not started
1 | Foundation | 1.2 | NestJS API scaffold + ConfigModule + TypeORM connection | 1 | 2 | 2 | 1.1 | apps/api scaffolded; main.ts (CORS, ValidationPipe, exception filter, Swagger at /docs); app.module.ts; config/configuration.ts (Joi); database/database.module.ts (TypeOrmModule.forRootAsync, PostGIS-aware); common/{guards,decorators,filters,interceptors,pipes}/ plumbing. | npm run start:dev shows 'Nest application successfully started'; GET /docs loads Swagger; GET /healthz returns {status:ok}. | Not started
1 | Foundation | 1.3 | Initial migration + seed script | 1 | 3 | 3 | 1.2 | Migration 1700000000000-init.ts creating 13 tables (users, otps, zones, stores, cylinders, stock_movements, drivers, distributors, pricing_rules, orders, order_events, payments, returns) with PostGIS extension + spatial indexes; seed.ts with 1 admin, 3 Karachi zones, 2 stores, 50 cylinders, 1 distributor, 2 drivers; npm scripts migration:run / migration:revert / seed; docs/database-schema.md. | npm run migration:run + npm run seed succeed; psql \dt shows 13 tables; select count(*) from zones = 3; select postgis_version() returns 3.3.x. | Not started
2 | Auth & Users | 2.1 | Auth module - OTP + JWT | 1 | 4 | 4 | 1.3 | modules/auth (controller, service, module); POST /auth/otp/send and POST /auth/otp/verify; JwtStrategy, JwtAuthGuard, RolesGuard, @CurrentUser, @Roles; DTOs validated with class-validator. | OTP send returns 201, code appears in API logs (mock provider); OTP verify returns accessToken; JWT decodes to {sub, role}. | Not started
2 | Auth & Users | 2.2 | Users module + role-protected route demo | 1 | 5 | 5 | 2.1 | modules/users (controller, service, module, user.entity.ts); GET /users/me (JWT), PATCH /users/me, GET /users (admin only); e2e spec for role guard. | GET /users/me returns 200 for any user; GET /users returns 403 for non-admin and 200 for admin. | Not started
3 | Geographic & Inventory Core | 3.1 | Zones module - PostGIS polygons | 1 | 6 | 6 | 2.2 | modules/zones with zone.entity.ts (geography(Polygon,4326), PolygonTransformer); POST /zones (admin) GeoJSON polygon; GET /zones; GET /zones/lookup?lat=&lng= using ST_Contains; Karachi polygons in seed. | GET /zones/lookup?lat=24.8138&lng=67.0299 returns Clifton; out-of-bounds coords return 404. | Not started
3 | Geographic & Inventory Core | 3.2 | Stores + Inventory | 1 | 7 | 7 | 3.1 | modules/stores (POST/GET /stores, ?zoneId= filter, auto-zone from point); modules/inventory (cylinder.entity, stock-movement.entity, GET /inventory/stores/:id, POST /inventory/movements). | GET /stores returns 2 seeded stores; GET /inventory/stores/:id shows cylinder counts by state and size; movement endpoint shifts counts. | Not started
3 | Geographic & Inventory Core | 3.3 | Pricing module | 1 | 8 | 8 | 3.2 | modules/pricing with pricing-rule.entity.ts; GET /pricing/quote (from/to zone, km, cylinder size & count); fallback to source-zone defaults; seed rules. | GET /pricing/quote returns {flatFee, perKmFee, total} matching seeded rules. | Not started
4 | Orders & Dispatch | 4.1 | Orders module - CRUD + state machine | 1 | 9 | 9 | 3.3 | modules/orders with state machine (PENDING/CONFIRMED/ASSIGNED/IN_TRANSIT/DELIVERED/CANCELLED); POST /orders resolves zone via ST_Contains, quotes fee, emits BullMQ order.created; GET /orders/me, GET /orders/:id, PATCH /orders/:id/status; order_events audit row. | POST /orders returns 201 with zoneId and deliveryFee; GET /orders/me lists it; status transitions enforced (illegal -> 400). | Not started
4 | Orders & Dispatch | 4.2 | Drivers module + Socket.io gateway | 1 | 10 | 10 | 4.1 | modules/drivers (driver.entity, POST /drivers/me/location, PATCH /drivers/me/availability); drivers.gateway.ts Socket.io namespace /drivers with JWT auth; current_zone_id recomputed via ST_Contains on each update. | Driver POST location updates DB and current_zone_id; socket client connects with JWT and emits location:update successfully. | Not started
4 | Orders & Dispatch | 4.3 | Dispatch - scoring + BullMQ worker | 1 | 11 | 11 | 4.2 | dispatch.service.ts scoring algorithm (distance to nearest stocked store, store->client, capacity, same-zone bonus); dispatch.processor.ts BullMQ consumer assigns top driver, transitions order ASSIGNED, emits Socket.io order:assigned; POST /dispatch/run/:orderId admin endpoint; docs/dispatch-algorithm.md. | Placing an order results in status=ASSIGNED with assignedDriverId & assignedStoreId within ~1s; worker logs show scores. | Not started
5 | Payments, Returns, Notifications | 5.1 | Payments + Returns | 1 | 12 | 12 | 4.3 | modules/payments (POST /payments distributor, POST /payments/:id/confirm admin) updates distributors.advance_balance_pkr; modules/returns (POST /returns, PATCH /returns/:id/pickup) moves cylinders to EMPTY at store. | Submit payment -> pending; admin confirm -> balance increases by amount; return pickup transitions cylinder states. | Not started
5 | Payments, Returns, Notifications | 5.2 | Notifications module (in-app & FCM stub) | 1 | 13 | 13 | 5.1 | modules/notifications with FcmProvider + SmsProvider interfaces; Mock providers; hooked into order lifecycle events; notifications Postgres table; GET /notifications/me. | Order events log mock FCM payload; GET /notifications/me returns in-app notifications for the user. | Not started
6 | Third-party Integrations | 6.1 | Twilio / Africa's Talking SMS | 1 | 14 | 14 | 5.2 | Twilio and Africa's Talking SMS providers; SMS_PROVIDER env switch; factory in NotificationsModule; real OTP delivered when creds present. | With AT/Twilio creds set, OTP send delivers real SMS to a test phone; missing creds falls back to mock with warning log. | Not started
6 | Third-party Integrations | 6.2 | Firebase Cloud Messaging push | 1 | 15 | 15 | 6.1 | fcm.provider.ts using firebase-admin; users.fcm_token column + POST /users/me/fcm-token; order lifecycle pushes real FCM when token present. | Register FCM token from device, place an order, push notification arrives; API logs show FCM message_id. | Not started
6 | Third-party Integrations | 6.3 | JazzCash payment gateway | 1 | 16 | 16 | 6.2 | jazzcash.provider.ts with HMAC-SHA256 secure hash; POST /payments/jazzcash/initiate returns redirect params; POST /payments/jazzcash/callback verifies and confirms; manual flow preserved. | JazzCash sandbox payment completes and callback marks payment CONFIRMED automatically. | Not started
6 | Third-party Integrations | 6.4 | Easypaisa + Google Maps + MinIO uploads | 1 | 17 | 17 | 6.3 | easypaisa.provider.ts mirrors JazzCash; Google Maps key wired into Expo app.json extras (MapView renders real tiles); MinIO bucket auto-create + POST /storage/upload. | Easypaisa sandbox completes; mobile map renders real tiles around Karachi; image upload returns S3 URL visible in MinIO console. | Not started
7 | Mobile - Customer | 7.1 | Expo scaffold + auth screens + API client | 1 | 18 | 18 | 6.4 | apps/mobile scaffolded TS; deps installed; src/api/client.ts (Axios + JWT interceptor from expo-secure-store); auth.api.ts; authStore.ts; PhoneScreen, OtpScreen; RootNavigator with role-based switch. | npx expo start; enter phone, receive mock OTP from logs, verify, land on Customer Home; JWT persists in SecureStore. | Not started
7 | Mobile - Customer | 7.2 | Place Order + Track Order | 1 | 19 | 19 | 7.1 | HomeScreen (CTA + active order banner); PlaceOrderScreen (map picker, cylinder size/count, fee quote); TrackOrderScreen (status stepper + driver location via Socket.io); shared components OrderCard, StatusStepper, MapView. | Place an order in app, see live fee, confirm; Track screen shows driver pin moving as driver app pushes locations. | Not started
7 | Mobile - Customer | 7.3 | Order History + polish | 1 | 20 | 20 | 7.2 | OrderHistoryScreen (paginated, pull-to-refresh); ProfileScreen; empty/error/loading states; push token registration on first launch. | Place 3 orders -> history shows 3; force close + reopen -> still logged in; placing order triggers push notification. | Not started
8 | Mobile - Distributor | 8.1 | Distributor Dashboard + Orders list | 1 | 21 | 21 | 7.3 | DashboardScreen with KPIs (today's orders, advance balance); OrdersListScreen with status filter, accept/reject actions; DistributorStack. | Customer places order -> distributor dashboard updates KPI; distributor accepts -> order CONFIRMED. | Not started
8 | Mobile - Distributor | 8.2 | Inventory + Payments management | 1 | 22 | 22 | 8.1 | InventoryScreen with per-store cylinder counts and request-restock; PaymentsScreen submit advance payment proof (image upload to MinIO) + ledger view. | Inventory counts match DB; submit payment with image -> admin confirms -> balance updates in distributor app. | Not started
9 | Mobile - Driver | 9.1 | Driver Home + Active delivery | 1 | 23 | 23 | 8.2 | DriverHomeScreen with online/offline toggle + current assignment; ActiveDeliveryScreen with pickup + delivery actions, navigation hand-off; DriverStack. | Driver online -> receives assignment; Picked Up -> IN_TRANSIT; Delivered -> DELIVERED with customer push. | Not started
9 | Mobile - Driver | 9.2 | Live location push + offline resilience | 1 | 24 | 24 | 9.1 | expo-location background task every 10s POSTs to /drivers/me/location and emits via socket; offline queue batches updates; battery-conscious throttle. | Walking with app online updates customer's Track screen pin; offline for 30s then back online -> backlog flushes. | Not started
10 | Backend Testing | 10.1 | Unit tests for service layer | 1 | 25 | 25 | 9.2 | *.service.spec.ts for auth, users, zones, stores, inventory, pricing, orders, drivers, dispatch (scoring), payments, returns; mocked repos; >=70% coverage on services. | npm test -- --coverage all green; coverage report shows >=70% statements on service files. | Not started
10 | Backend Testing | 10.2 | e2e tests for HTTP API | 1 | 26 | 26 | 10.1 | test/*.e2e-spec.ts for auth, orders, dispatch, payments etc.; dedicated test DB created in beforeAll; happy paths + 401/403 + invalid input. | npm run test:e2e all green. | Not started
10 | Backend Testing | 10.3 | Dispatch property tests + load smoke | 1 | 27 | 27 | 10.2 | dispatch.property-spec.ts with fast-check (same-zone bonus invariant etc.); k6 script for 50 concurrent customers placing orders. | Property tests green; k6 reports p95 < 500ms and 0 errors. | Not started
11 | Maps & Routing | 11.1 | OSRM self-hosted routing + ETA | 1 | 28 | 28 | 10.3 | docker-compose adds osrm service with Pakistan extract; routing.service.ts queries OSRM for road distance; mobile Track screen shows polyline route. | curl http://localhost:5000/route/v1/... returns real distance; dispatch logs show OSRM-based scoring; mobile shows route polyline. | Not started
12 | Production Hardening | 12.1 | Observability + security | 1 | 29 | 29 | 11.1 | pino structured logging + request-id middleware; /healthz liveness, /readyz checks DB+Redis; @nestjs/throttler rate limit on auth; helmet + CORS allow-list + body size limit; Sentry SDK API + mobile. | 20 rapid /auth/otp/send -> 429; readyz returns 503 when DB stopped; crashed request appears in Sentry. | Not started
12 | Production Hardening | 12.2 | Backups, secrets, env templating | 1 | 30 | 30 | 12.1 | infrastructure/scripts/backup.sh pg_dump + optional rclone; docker-compose.prod.yml uses env_file; .env.prod.example; migrations are an explicit deploy step. | backup.sh produces dated dump under infrastructure/backups/; gunzip -t passes. | Not started
13 | Deployment | 13.1 | VPS provision + first deploy | 1 | 31 | 31 | 12.2 | scripts/provision.sh (Docker + UFW + fail2ban); nginx.conf with Let's Encrypt (certbot container); docker-compose.prod.yml full stack; docs/deploy.md runbook. | On fresh Ubuntu 24.04 VPS: provision + docker compose up succeeds; external HTTPS curl to /healthz works. | Not started
13 | Deployment | 13.2 | Mobile build + store submission prep | 1 | 32 | 32 | 13.1 | eas.json release profiles (Android .aab, iOS .ipa); app icons + splash; store screenshots; listing copy in docs/store-listing.md; internal testing tracks set up. | eas build --platform android --profile production produces .aab; installed on test device runs against prod API. | Not started
14 | Buffer | B.1 | Buffer / rework day 1 | 1 | 33 | 33 | 13.2 | Reserved for bug fixes from milestone reviews, schema migrations after early data, provider-specific quirks. | Green CI + smoke test of any flow touched. | Not started
14 | Buffer | B.2 | Buffer / rework day 2 | 1 | 34 | 34 | B.1 | Reserved (see B.1). | Green CI + smoke test of any flow touched. | Not started
14 | Buffer | B.3 | Buffer / rework day 3 | 1 | 35 | 35 | B.2 | Reserved (see B.1). | Green CI + smoke test of any flow touched. | Not started

## Gantt
Task ID | Task Name | Phase | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35
1.1 | Bootstrap monorepo + infrastructure | Foundation | X
1.2 | NestJS API scaffold + ConfigModule + TypeORM connection | Foundation |  | X
1.3 | Initial migration + seed script | Foundation |  |  | X
2.1 | Auth module - OTP + JWT | Auth & Users |  |  |  | X
2.2 | Users module + role-protected route demo | Auth & Users |  |  |  |  | X
3.1 | Zones module - PostGIS polygons | Geographic & Inventory Core | [5 empty] | X
3.2 | Stores + Inventory | Geographic & Inventory Core | [6 empty] | X
3.3 | Pricing module | Geographic & Inventory Core | [7 empty] | X
4.1 | Orders module - CRUD + state machine | Orders & Dispatch | [8 empty] | X
4.2 | Drivers module + Socket.io gateway | Orders & Dispatch | [9 empty] | X
4.3 | Dispatch - scoring + BullMQ worker | Orders & Dispatch | [10 empty] | X
5.1 | Payments + Returns | Payments, Returns, Notifications | [11 empty] | X
5.2 | Notifications module (in-app & FCM stub) | Payments, Returns, Notifications | [12 empty] | X
6.1 | Twilio / Africa's Talking SMS | Third-party Integrations | [13 empty] | X
6.2 | Firebase Cloud Messaging push | Third-party Integrations | [14 empty] | X
6.3 | JazzCash payment gateway | Third-party Integrations | [15 empty] | X
6.4 | Easypaisa + Google Maps + MinIO uploads | Third-party Integrations | [16 empty] | X
7.1 | Expo scaffold + auth screens + API client | Mobile - Customer | [17 empty] | X
7.2 | Place Order + Track Order | Mobile - Customer | [18 empty] | X
7.3 | Order History + polish | Mobile - Customer | [19 empty] | X
8.1 | Distributor Dashboard + Orders list | Mobile - Distributor | [20 empty] | X
8.2 | Inventory + Payments management | Mobile - Distributor | [21 empty] | X
9.1 | Driver Home + Active delivery | Mobile - Driver | [22 empty] | X
9.2 | Live location push + offline resilience | Mobile - Driver | [23 empty] | X
10.1 | Unit tests for service layer | Backend Testing | [24 empty] | X
10.2 | e2e tests for HTTP API | Backend Testing | [25 empty] | X
10.3 | Dispatch property tests + load smoke | Backend Testing | [26 empty] | X
11.1 | OSRM self-hosted routing + ETA | Maps & Routing | [27 empty] | X
12.1 | Observability + security | Production Hardening | [28 empty] | X
12.2 | Backups, secrets, env templating | Production Hardening | [29 empty] | X
13.1 | VPS provision + first deploy | Deployment | [30 empty] | X
13.2 | Mobile build + store submission prep | Deployment | [31 empty] | X
B.1 | Buffer / rework day 1 | Buffer | [32 empty] | X
B.2 | Buffer / rework day 2 | Buffer | [33 empty] | X
B.3 | Buffer / rework day 3 | Buffer | [34 empty] | X

## Critical Files
Path | Why it matters
apps/api/src/database/migrations/1700000000000-init.ts | Full schema (13 tables, PostGIS extension, spatial indexes)
apps/api/src/modules/auth/auth.service.ts | OTP issue/verify, JWT signing
apps/api/src/modules/orders/orders.service.ts | Order lifecycle, fee quoting, dispatch enqueue
apps/api/src/modules/dispatch/dispatch.service.ts | Driver scoring algorithm (core of the product)
apps/api/src/modules/dispatch/dispatch.processor.ts | BullMQ worker that assigns drivers
apps/api/src/modules/drivers/drivers.gateway.ts | Socket.io live location gateway
packages/shared-types/src/*.ts | TS contracts shared by API + mobile
packages/shared-utils/src/haversine.ts | Distance calc used in scoring + mobile ETA
apps/mobile/src/api/client.ts | Axios + JWT interceptor
apps/mobile/src/navigation/RootNavigator.tsx | Role-based routing
infrastructure/docker-compose.yml | Dev stack (Postgres+PostGIS, Redis, MinIO, OSRM)
infrastructure/docker-compose.prod.yml | Prod stack incl. nginx + certbot
infrastructure/nginx/nginx.conf | TLS termination + reverse proxy

## Risks
Risk | Mitigation
Provider sandbox credentials slow to obtain (JazzCash, Easypaisa, Twilio) | Phase 6 can slip; mocks remain functional, mobile dev unblocked
OSRM Pakistan extract is ~1GB and slow to bootstrap | Pre-build a Docker image with extract baked in; cache locally
iOS provisioning profile drama for first build | Use EAS managed credentials; Android first, iOS as buffer task
Real load > 50 concurrent on single VPS | k6 baseline in 10.3 sets the budget; if exceeded, plan a follow-up scale-out milestone (managed Postgres, separate worker)
PostGIS columns require explicit TypeORM transformers | Custom PointTransformer + PolygonTransformer in shared util; covered by unit tests
Mobile + API monorepo install can be 1-2GB | Use npm workspaces hoisting; CI caches; document disk requirement