## README
Smart_Fleet — Pilot Test Plan
◼ | Purpose
Atomic test cases for the AWS pilot deployment (smartfleetpk.com).
Every row = one observable outcome. Pass/fail is unambiguous.
Designed to run grouped, not one-at-a-time, so you cover most features in the FEWEST APK rebuilds.
◼ | How to use
1. Open the 'Test Groups' tab. Each group is one sitting (15–45 min) and is independent of every other group.
2. Pick a group based on what you can test right now (e.g. distributor-only, or only when a driver is available).
3. Run every Atomic Case in that group's range, marking Result + Actual.
4. Anything that requires a code change goes into the 'Build Backlog' tab so it ships in the NEXT rebuild, not a new one each time.
5. Field scenarios (the ones that need a real motorbike + sun + a damaged QR sticker) live in their own tab — schedule them.
◼ | Why grouped this way
Each group shares 'setup state' — one login, one client, one order — and exercises many features off that shared state.
Groups never depend on each other. You can run Group G (admin) without Groups A–F.
Field groups (J, K) deliberately run LAST so all desk bugs are out of the way before motorbikes get involved.
◼ | Reading OTPs in pilot (mock SMS)
EC2: sudo docker logs smartfleet-api-prod --since 2m ¦ grep -A4 'OTP-MOCK'
The 6-digit code is in the 'msg:' line. Codes expire in 5 minutes; only the most recent works.
◼ | Test accounts (replace at go-live)
Super admin (web, password): +923000000000 / ChangeMe!Now123
Branch admin (web, password): +923000000001 / ChangeMe!Now123
Distributor (mobile, OTP): +923001111111
Driver (mobile, OTP): +923002222222
Walk-in client phone: +923009999999
◼ | Severity legend
P0 (red) — blocks pilot; must pass before letting any real user touch the system.
P1 (amber) — should pass; workaround acceptable for ≤1 week.
P2 (blue) — nice-to-have; track but don't block.
◼ | Outcome legend
PASS — actual matches expected exactly.
FAIL — actual differs; write what you saw in 'Actual'.
BLOCKED — couldn't run (e.g. waiting on a driver). Note why.
N/A — not applicable for this environment/build.

## Test Groups
Group | Name | Duration | Where | Pre-requirements | What it covers | Rebuild needed? | Depends on
A | Cold-Start + Auth (admin + mobile) | 20 min | Desk | Distributor APK installed, admin web reachable | Login screens, OTP flow, password flow, token persistence, idle/explicit logout, negative auth, role isolation at login | No (run as-is) | —
B | Distributor — Add Client + Address Search | 20 min | Desk | Logged in as distributor | Client form validation, duplicate prevention, address-search edge cases (English/Urdu/rural/urban), map-stub render, save-and-revisit | No | A
C | Distributor — Place Order (matrix) | 30 min | Desk | Group B done (at least 1 client), cylinder types seeded | Cart math, single/multi-type orders, empty-return quantities, address autofill from client, submit, rejection paths | No | B
D | Distributor — History, Track, Ledger, Inventory | 20 min | Desk | ≥3 orders from Group C | Order history pagination/filters, tracking status flow, ledger entries, inventory counts, balance display, refresh behaviour | No | C
E | Admin Web — Operations & Order Lifecycle | 30 min | Desk | Orders from Group C | Dashboard KPIs, order assignment, status transitions, role-restricted actions, distributor/driver/vehicle CRUD, live deliveries | No (admin web hot-deployable via S3 sync) | C
F | Admin Web — Master Data CRUD | 30 min | Desk | Admin login | Cities, zones, stores, cylinder types, accessories, pricing rules, filling stations, drivers, vehicles. Create + edit + soft-delete each. | No | —
G | Driver — Receive, Scan, Deliver, Return | 30 min | Desk first, then yard | Driver APK installed (when ready), printed cylinder QR codes (use admin's QR generator), driver assigned to a vehicle | Trip acceptance, sequential custody scans, proof photo upload, status transitions, location pings appearing in admin live map | Driver APK only (one-time) | E (driver assigned)
H | Network Resilience | 20 min | Desk | Distributor app + airplane-mode-capable phone | Action on full offline, action on flaky/3G, server-side 5xx response, expired token mid-request, app behaviour when API is restarting | Defensive guards may queue → next rebuild | B
I | Security & Permissions | 30 min | Desk | Two distributor accounts, admin login, browser dev tools | Cross-distributor data isolation, role-restricted endpoints reject wrong roles, token tampering rejected, S3 not publicly listable, OTP not leaked in prod, PII encrypted at rest | No (server-side) | C, E
J | FIELD — Driver Day-in-the-Life | ≥1 work day | Real route on a motorbike | Driver APK final build, real distributor, real customer (consenting test customer), real cylinder with real QR sticker | Sun glare, dust, gloves, helmet ear-noise on notifications, GPS accuracy in tight alleys, battery drain over a shift, photo quality at dusk, custody-scan on a worn label, mobile signal drops between deliveries | Findings go into Build Backlog → batched into ONE rebuild at end of day | G
K | FIELD — Distributor Operations | ≥1 work day | Real shop | Distributor APK final build, real customer phone numbers (with consent) | Phone-input ergonomics on cheap Androids, OTP delivery delay perception, order entry under customer time-pressure, screen visibility under tube light, back-button confusion, network handoff WiFi↔SIM | Same as Group J | C
L | Multi-Day Soak + OTA | 3–5 days elapsed | Desk + field | All apps installed and in use; one OTA fix scheduled in the middle | Refresh token rollover, day-boundary edge cases (orders crossing midnight), OTA update delivery + auto-apply, log noise & alarm health, cost steady at ~$0/day | Test OTAs without rebuild; one rebuild at end if anything native broke | G, J

## Atomic Cases
TC-ID | Group | Priority | Area | Surface | Test Case | Pre-condition | Steps | Expected Outcome | Tested on | Type | Result (PASS/FAIL/BLOCKED/NA) | Actual Result | Defect ID | Tester | Date | Notes
Group A — Cold-Start + Auth (admin + mobile)
A01 | A | P0 | Auth | Admin web | Admin web loads without console errors | Browser cache cleared; production URL up. | 1. Open https://admin.smartfleetpk.com 2. Open DevTools → Console. | Login screen renders; no red console errors; bundle filename in Network ≠ a stale broken one. | Admin web | Positive
A02 | A | P0 | Auth | Admin web | Super-admin signs in with valid password | Seed run; default password ChangeMe!Now123 known. | 1. Enter +923000000000 + correct password 2. Submit. | Lands in Dashboard within 3s; sidebar visible. | Admin web | Positive
A03 | A | P0 | Auth | Admin web | Wrong password is rejected with same message every time | — | Try (a) wrong password (b) unknown phone +923444444444 (c) blank password. | All three return the exact same 'Invalid phone or password' (no enumeration leak); no dashboard. | Admin web | Negative
A04 | A | P1 | Auth | Admin web | Distributor phone with any password is rejected with role hint | +923001111111 exists as DISTRIBUTOR. | Sign in with +923001111111 + any password. | Server returns 'must sign in with a one-time code, not a password'. Login fails. | Admin web | Negative
A05 | A | P1 | Auth | Admin web | Token persists across browser refresh | Logged in as super-admin. | Reload the tab (Ctrl+R). | Still on Dashboard; no re-login required. | Admin web | Positive
A06 | A | P1 | Auth | Admin web | Explicit logout clears token + returns to login | Logged in. | Click Logout from sidebar/profile menu. | Login screen shown; refreshing does not auto-login. | Admin web | Positive
A07 | A | P2 | Auth | Admin web | Idle logout after configured timeout | Logged in. Site sets 10-min idle. | Leave the tab focused but untouched for >10 min (cheat by editing the constant in dev if testing in <10). | Auto-redirects to login. | Admin web | Edge
A08 | A | P0 | Auth | Distributor app | OTP send returns success | Distributor user +923001111111 exists and is ACTIVE. | Open app → enter +923001111111 → Send OTP. | App shows 'code sent' state; logs on EC2 show an OTP-MOCK block for +923001111111. | Distributor app | Positive
A09 | A | P0 | Auth | Distributor app | OTP verify with fresh code succeeds | A09 immediately after A08 (within 5 min). | Read code from logs → enter → submit. | Lands in distributor home; bottom tabs/main screen visible. | Distributor app | Positive
A10 | A | P1 | Auth | Distributor app | Stale OTP is rejected | Wait >5 min after a send, or send a NEW OTP then try the OLD code. | Submit the older code. | Error 'OTP expired or not found' OR 'Invalid code'; not logged in. | Distributor app | Negative
A11 | A | P1 | Auth | Distributor app | Rate limit kicks in after 3 sends in 60s | Fresh phone with no recent OTPs. | Tap Send OTP four times within 30s. | 4th request returns 'Too many OTP requests'; client shows error. | Distributor app | Negative
A12 | A | P1 | Auth | Distributor app | Login state survives app cold-start | Logged in. | Force-stop the app, reopen. | Back on home screen without re-OTP. | Distributor app | Positive
A13 | A | P1 | Auth | Driver app | Driver OTP login (same flow as distributor) | +923002222222 exists as DRIVER with Driver profile. | Repeat A08–A09 with driver phone using driver APK. | Lands in driver home; trip queue/idle state visible. | Driver app | Positive
Group B — Distributor — Add Client + Address Search
B01 | B | P0 | Clients | Distributor app | Add Client screen opens without crash | Logged in. | Tap Add Client. | Form opens; MapStub card visible where map used to be; no white screen / no app exit. | Distributor app | Positive
B02 | B | P0 | Clients | Distributor app | Save a valid client | Add Client open. | Name='Asma Naveed', Phone='+923211234567', Area='G-13', City='Islamabad', address search → pick a suggestion. Save. | Toast/success; client appears in client list. | Distributor app | Positive
B03 | B | P1 | Clients | Distributor app | Phone is validated as E.164 | Add Client open. | Type '03001234567' (no country code) → Save. | Inline error or rejection; not saved. | Distributor app | Negative
B04 | B | P1 | Clients | Distributor app | Address search returns Pakistani results | Add Client open, search field focused. | Type 'F-7 Markaz Islamabad'. | Suggestions appear within ~3s; pick top → lat/lng visible in marker card. | Distributor app | Positive
B05 | B | P2 | Clients | Distributor app | Address search handles ambiguous query gracefully | — | Search 'abc'. | Either no results message OR an empty list; no crash, no infinite spinner. | Distributor app | Edge
B06 | B | P1 | Clients | Distributor app | Duplicate phone is prevented | Client from B02 saved. | Add another client with same phone. | Server rejects with a clear error; UI shows it. | Distributor app | Negative
B07 | B | P1 | Clients | Distributor app | Saved client persists across app restart | B02 done. | Force-stop app → reopen → go to client list. | Client still listed. | Distributor app | Positive
B08 | B | P2 | Clients | Distributor app | Client list searchable by name and phone | ≥3 clients in list. | Type partial name; then partial phone. | Filtered results match; clearing search restores list. | Distributor app | Positive
Group C — Distributor — Place Order (matrix)
C01 | C | P0 | Orders | Distributor app | New Order screen opens | Logged in; ≥1 client + 4 cylinder types seeded. | Tap New Order. | 'Who' step shows; client search field focused; no crash. | Distributor app | Positive
C02 | C | P0 | Orders | Distributor app | Order with one cylinder type submits | C01. | Search 'Walk' → pick Walk-in Customer; address autofill OR re-search; cylinder 'LPG 11.8 kg' qty=1, empty-return=0; Submit. | Success screen; new order id printed; appears in My Orders as PENDING. | Distributor app | Positive
C03 | C | P0 | Orders | Distributor app | Order with multiple cylinder types | — | Add LPG 11.8 (qty 2), LPG 6 (qty 1); empties returned = 1 of LPG 11.8. Submit. | Single order created with 2 lines; quantities exactly as entered in My Orders detail. | Distributor app | Positive
C04 | C | P1 | Orders | Distributor app | Cart math: increment / decrement / remove | Cart with mixed items. | +/- buttons; remove a line; re-add same type. | On-screen totals stay consistent with what you submit. No negative quantities. | Distributor app | Edge
C05 | C | P0 | Orders | Distributor app | Cannot submit empty cart | Cart empty. | Try Submit. | Submit disabled or rejected with a message; no order created. | Distributor app | Negative
C06 | C | P1 | Orders | Distributor app | Cannot submit with no client | Cart has items, client step skipped. | Try Submit. | Blocked; prompt to pick a client. | Distributor app | Negative
C07 | C | P1 | Orders | Distributor app | Address picked from address search saves on the order | — | Place an order using a different address than the client's default. | Admin web Orders detail shows the picked address, not the client's default. | Distributor app | Positive
C08 | C | P1 | Orders | Distributor app | Back navigation does not lose cart | Cart with 2 items. | Back to 'Who' step; pick a different client; come forward. | Cart intact (or behaviour matches expected design); no orphan order. | Distributor app | Edge
C09 | C | P2 | Orders | Distributor app | Submit while network drops | Cart ready; toggle airplane mode at moment of Submit. | Tap Submit with airplane mode on. | Clear error; no half-created order on server; retry succeeds after reconnect. | Distributor app | Edge
Group D — Distributor — History, Track, Ledger, Inventory
D01 | D | P0 | History | Distributor app | Order History lists today's orders | ≥3 orders placed today. | Open Order History. | All 3 visible, newest first; correct status badges. | Distributor app | Positive
D02 | D | P1 | History | Distributor app | Pull-to-refresh updates state | Admin changes one order's status in web. | Pull down to refresh in app. | Status updates without app restart. | Distributor app | Positive
D03 | D | P0 | Track | Distributor app | Track Order screen opens without map crash | Tap an active order. | Open Track. | Screen renders; MapStub card visible; no app exit. | Distributor app | Positive
D04 | D | P1 | Ledger | Distributor app | Ledger entries reflect order activity | Pricing rules configured (admin) → otherwise mark N/A. | Open Ledger. | Entries present for placed orders OR explicit 'no activity' state; balance arithmetic correct. | Distributor app | Positive
D05 | D | P1 | Inventory | Distributor app | Inventory shows current full/empty counts | Custody seeded or after Group G. | Open Inventory. | Counts shown by cylinder type; refresh consistent with admin view. | Distributor app | Positive
Group E — Admin Web — Operations & Order Lifecycle
E01 | E | P0 | Dashboard | Admin web | KPI tiles populate | Seed + Groups C ran. | Open Dashboard. | Tiles render (zero or non-zero values), no console errors. | Admin web | Positive
E02 | E | P0 | Dashboard | Admin web | Recent orders include the latest distributor order | Place an order in app, wait <30s. | Refresh Dashboard. | Order id matches; correct distributor + client + status PENDING. | Admin web | Positive
E03 | E | P0 | Orders | Admin web | Assign order to driver | Order PENDING; driver record exists. | Open order → Assign → pick driver → Save. | Status changes to ASSIGNED; driver attached; activity log updated. | Admin web | Positive
E04 | E | P1 | Orders | Admin web | Illegal status jump rejected by API | Order PENDING. | Use dev tools or admin UI to push status DELIVERED directly. | Server rejects with a clear error; order stays PENDING. | Admin web | Negative
E05 | E | P1 | Orders | Admin web | Cancel order updates status | Order PENDING. | Cancel from admin web. | Status CANCELLED; reflected in distributor app on refresh. | Admin web | Positive
E06 | E | P1 | Live | Admin web | Live Deliveries screen loads | — | Open Live screen. | Map area + driver list render; no console errors. (Driver markers may be empty if no drivers online.) | Admin web | Positive
E07 | E | P1 | Live | Admin web | Driver location appears when driver is online | Group G running. | Driver online → admin watches. | Marker appears within ~30s and updates as driver moves. | Admin web | Positive
E08 | E | P2 | Live | Admin web | Tab away + return reconnects socket | Live screen open with driver online. | Switch tabs for 1 min; return. | Socket reconnects; latest location shown. | Admin web | Edge
Group F — Admin Web — Master Data CRUD
F01 | F | P0 | Cities | Admin web | List cities (seeded) | Seed ran. | Open Cities. | Islamabad / Rawalpindi / Lahore / Karachi visible. | Admin web | Positive
F02 | F | P1 | Zones | Admin web | Create a zone with a polygon | City exists. | New Zone → name → draw polygon → save. | Zone saved with PostGIS polygon; appears on map. | Admin web | Positive
F03 | F | P1 | Stores | Admin web | Create a store under a zone | Zone from F02. | New Store → fill fields → Save. | Store listed; assignable to drivers/orders. | Admin web | Positive
F04 | F | P0 | Cylinder types | Admin web | Cylinder types editable | Seed types exist. | Edit a type's display name. | Saved; updated name shows in distributor app after refresh. | Admin web | Positive
F05 | F | P1 | Pricing | Admin web | Create a pricing rule | City + cylinder type exist. | Pricing → New Rule → set price. | Rule listed; later orders use it. | Admin web | Positive
F06 | F | P1 | Vehicles | Admin web | Create a vehicle and assign driver | Driver exists. | Vehicles → New → plate / capacity → assign driver. | Vehicle + assignment saved; visible in Driver detail. | Admin web | Positive
F07 | F | P1 | Drivers | Admin web | Edit driver (e.g. set availability) | Driver record. | Edit availability ON_LEAVE; save. | Persists; dispatcher view reflects it. | Admin web | Positive
F08 | F | P1 | Distributors | Admin web | Suspend a distributor | Distributor record. | Suspend. | Suspended distributor cannot place new orders on mobile (returns auth/role error). | Admin web | Edge
F09 | F | P2 | Accessories | Admin web | List + create accessory | Seed accessories present. | Create a new accessory. | Saved; listed; pricing assignable. | Admin web | Positive
F10 | F | P2 | Filling stations | Admin web | Create a filling station | — | New filling station. | Saved + listed. | Admin web | Positive
Group G — Driver — Receive, Scan, Deliver, Return
G01 | G | P0 | Driver | Driver app | Driver sees assigned trip | E03 happened (order ASSIGNED). | Open driver app. | Assigned trip listed; tapping opens its details. | Driver app | Positive
G02 | G | P0 | Custody | Driver app | Scan cylinder QR at store pickup | Printed test QR sticker generated by admin's QR generator. | Open camera; scan the QR. | Custody event created (VEHICLE); count increments. | Driver app | Positive
G03 | G | P0 | Custody | Driver app | Scan unrecognized QR is rejected | Random QR. | Scan a non-Smart_Fleet QR. | Inline error 'not recognized'; no custody event created. | Driver app | Negative
G04 | G | P1 | Custody | Driver app | Re-scan of the same cylinder is debounced | Cylinder already VEHICLE. | Scan it again. | No duplicate event OR a clear 'already in custody' message. | Driver app | Edge
G05 | G | P0 | Delivery | Driver app | Mark delivered + capture proof photo | At delivery step. | Capture proof photo → confirm. | Photo uploads to S3 (smartfleet-files-prod) — verify in admin order detail. | Driver app | Positive
G06 | G | P0 | Delivery | Driver app | Delivered status reflects on distributor + admin | After G05. | Refresh distributor + admin views. | Order status DELIVERED everywhere within ~30s. | Distributor app / Admin web | Positive
G07 | G | P1 | Custody | Driver app | Pick up empty cylinder back to vehicle | Customer hands over empty cylinder QR. | Scan empty in. | Custody event captures empty; counts adjust. | Driver app | Positive
G08 | G | P1 | Trip | Driver app | End trip / return to store | All stops complete. | Mark trip complete. | Trip COMPLETED; driver shows AVAILABLE again on admin. | Driver app | Positive
G09 | G | P1 | Location | Driver app | Live location pings reach admin | Driver online + permission granted. | Walk around for 60s. | Admin Live screen marker moves; data points stored. | Driver app + Admin web | Positive
Group H — Network Resilience
H01 | H | P1 | Network | Distributor app | Action on full offline shows friendly error | Distributor logged in. | Airplane mode ON → Send OTP/Place Order. | Specific 'no connection' message; UI not stuck on spinner; no crash. | Distributor app | Edge
H02 | H | P1 | Network | Distributor app | Slow 3G doesn't hang the app | Throttle to ~150 kbps using phone's slow-network shortcut OR a known weak-signal location. | Open List screens. | Skeleton/spinner shown; eventually loads; no white screen. | Distributor app | Edge
H03 | H | P1 | Network | Distributor app | 5xx from server shown clearly | Restart api-prod container while screen loads. | Trigger a list fetch during restart. | Error message + Retry button; no app exit. | Distributor app | Edge
H04 | H | P1 | Auth | Distributor app | Expired token triggers re-login | Tamper with stored token to expire it (dev only) OR wait past JWT TTL. | Trigger any authed call. | App redirects to login OR refreshes token silently and continues. | Distributor app | Edge
H05 | H | P0 | Resilience | EC2 | Container crash auto-restarts | SSH to EC2. | sudo docker kill smartfleet-api-prod | Container restarts within ~2s; /health/live returns ok within 10s. | API | Edge
H06 | H | P1 | Resilience | EC2 | After EC2 reboot, system is fully serving without manual steps | SSH access. | sudo reboot, wait, retest API + admin web + app. | All come back: Caddy HTTPS, containers up, app reconnects. | API + Admin web + Apps | Edge
Group I — Security & Permissions
I01 | I | P0 | Sec | API | Cross-distributor isolation | Two distributors A and B with their own clients. | Log in as A, hit /clients with A's token; then with B's token. | Each sees only their own clients; no overlap. | API | Negative
I02 | I | P0 | Sec | API | Role-restricted endpoint rejects wrong role | Distributor token in hand. | Call POST /orders/{id}/assign with distributor token. | 403 Forbidden. | API | Negative
I03 | I | P0 | Sec | API | Tampered JWT rejected | Valid token. | Flip one character in the signature; call /auth/me. | 401 Unauthorized; no role escalation. | API | Negative
I04 | I | P0 | Sec | S3 | S3 bucket cannot be listed publicly | Bucket name. | Open https://smartfleet-files-prod.s3.ap-southeast-1.amazonaws.com/ in incognito. | AccessDenied. (Files accessible only via app/pre-signed URLs.) | S3 | Negative
I05 | I | P0 | Sec | API | OTP NOT leaked in prod response | — | POST /auth/otp/send with phone in prod; inspect response. | Body is {ok:true} ONLY (no devCode). Compare to staging which DOES return devCode. | API | Positive
I06 | I | P1 | Sec | DB | PII encrypted at rest | SSH access; one user has CNIC stored. | Query users.cnic_encrypted in RDS. | Column is binary ciphertext, NOT readable plaintext. | DB | Positive
I07 | I | P1 | Sec | API | Suspended user cannot authenticate | Suspend +923001111111 from admin. | Try mobile OTP login. | Login refused with 'Account not active' (or equivalent). | API | Negative
Group J — FIELD — Driver Day-in-the-Life
J01 | J | P0 | Field | Driver app | App readable in direct midday sun | Real driver on bike, midday. | Read trip details + scan QR. | Driver can read screen without shading; if not, raise UI contrast issue. | Driver app | Field
J02 | J | P0 | Field | Driver app | QR scan on a worn / sun-faded sticker | Cylinder used for ~1 month with sticker outside. | Scan it. | Either reads OR shows a clear 'try again with light/closer' guidance. | Driver app | Field
J03 | J | P0 | Field | Driver app | Photo proof at dusk / low light | Real delivery at ~7pm. | Capture proof. | Photo legible OR app prompts to use torch; uploads succeed. | Driver app | Field
J04 | J | P0 | Field | Driver app | Battery drain over a 4-hour shift with location ON | Start at 100% battery; driver app foreground/background. | Use the app for 4 hours. | Battery drop ≤40% on a typical mid-range Android. Anything worse is a P1. | Driver app | Field
J05 | J | P1 | Field | Driver app | Backgrounded app continues to report location | Driver on the move; app in background. | Watch admin live map. | Location continues updating for at least 15 min in background. | Driver app + Admin web | Field
J06 | J | P1 | Field | Driver app | Mobile signal cuts in narrow alley → recovers | Known dead-zone street. | Pass through. | App holds the trip in memory, syncs scans/photos automatically when signal returns. | Driver app | Field
J07 | J | P1 | Field | Driver app | Notifications heard with helmet on / loud street | Helmet + bike sounds. | Receive a new order while riding. | Either sound is loud enough OR vibration is detectable on grip; or add a startup tip. | Driver app | Field
J08 | J | P1 | Field | Driver app | Glove-friendly buttons | Driver wears riding gloves. | Tap key buttons. | All primary actions tappable; no double-tap required. | Driver app | Field
J09 | J | P2 | Field | Driver app | GPS accuracy in dense urban | Run past 6-storey buildings in Karachi/Lahore. | Compare app marker to real position. | Drift ≤30m most of the time. Anything wilder → flag for future fix. | Driver app | Field
Group K — FIELD — Distributor Operations
K01 | K | P0 | Field | Distributor app | Phone-input ergonomics on a cheap Android | Test on a Rs. 25k Android (e.g. Vivo Y02 / Tecno). | Place an order under shop noise. | Form usable; no frame drops; full flow completes in ≤90s. | Distributor app | Field
K02 | K | P0 | Field | Distributor app | Reading OTP under tube light + dusty shop | Real distributor shop. | Distributor receives + reads OTP. (For pilot OTP comes via separate channel.) | Distributor can complete login within 60s of clicking Send. | Distributor app | Field
K03 | K | P1 | Field | Distributor app | Order entry under customer time-pressure | Customer at counter waiting. | Place order while talking to customer. | Distributor does not get blocked by validation; flow completes <60s. | Distributor app | Field
K04 | K | P1 | Field | Distributor app | Switch WiFi ↔ mobile data mid-action | Shop has both. | Begin order on WiFi; walk out (loses WiFi) before Submit. | App seamlessly continues over cellular; order saved correctly. | Distributor app | Field
K05 | K | P2 | Field | Distributor app | Back-button confusion | Distributor unfamiliar with Android nav. | Hand them the device, ask to place an order. | No 'I'm lost' moments; if they get stuck twice, raise a UI issue. | Distributor app | Field
K06 | K | P1 | Field | Distributor app | After full work day, app still responsive | Distributor places ≥30 orders over a day. | End-of-day open app. | No noticeable slowdown; lists render in <2s. | Distributor app | Field
Group L — Multi-Day Soak + OTA
L01 | L | P1 | Soak | Apps | Token still valid next morning | Logged in, leave overnight. | Reopen 12h later. | Either still logged in OR refresh-token flow runs silently. | Apps | Edge
L02 | L | P0 | OTA | Distributor app | EAS Update with a small JS change is picked up | Push a benign change (e.g. version label). | Run eas update --branch distributor-production; close + reopen app. | New change visible; old crash not back; runtime version match confirmed. | Distributor app | Positive
L03 | L | P1 | Cost | AWS Console | Day-over-day actual cost ≈ $0 | — | Billing → Bills, daily. | MTD actual cost stays under $1 even with active use; matches free-tier expectations. | AWS | Positive
L04 | L | P1 | Logs | CloudWatch | Errors don't drown the log group | — | CloudWatch /smartfleet/prod — daily glance. | <5 GB ingest/month overall; no recurring noisy error pattern. | CloudWatch | Positive
L05 | L | P1 | Alarms | CloudWatch | Alarms are not in ALARM state long-term | — | describe-alarms --alarm-name-prefix smartfleet-. | All OK or INSUFFICIENT_DATA; nothing chronic in ALARM. | CloudWatch | Positive
L06 | L | P2 | Day boundary | Apps | Orders crossing midnight handled | Place an order at 11:55 PM, deliver at 12:05 AM. | Inspect timestamps + 'Delivered today' KPI. | Delivered-today reflects the actual local date of delivery; no off-by-one. | Apps + Admin web | Edge

## Field Scenarios
FS-ID | Scenario | Who tests it | How | Pass criteria | Result | Notes / device | Tester | Date
FS-01 | Sun glare on screen | Drivers + distributors during 11am–4pm | Take both apps outside in direct sun. Time how long to find the next-step button. | Define brightness/contrast acceptable; if ≥1 user struggles ≥3 times → P1 fix.
FS-02 | Dust on camera lens | Driver bike rider | Don't wipe lens. Take 5 proof photos through dust. | Photos legible OR app prompts to wipe lens.
FS-03 | Worn / faded QR sticker | Real cylinders after 1+ month outdoor use | Scan deliberately damaged QRs. | App reads ≥80% of attempts. <80% → improve sticker material or QR error-correction level.
FS-04 | Background location while screen off | Driver app | Lock the phone for 15 min while moving. | Admin live map keeps receiving pings during that 15 min.
FS-05 | Helmet + bike noise on notifications | Driver | Push a new-assignment notification while riding. | Either heard via Bluetooth helmet speaker OR seen on next stop. Else add vibration pattern.
FS-06 | Glove-friendly tap targets | Driver wearing summer gloves | Tap every primary action (scan, capture, mark delivered). | All hit on first attempt. Else raise minimum tap-target size.
FS-07 | Cheap-Android performance | Distributor on Rs. 20–30k device | Test on at least one budget Android (e.g. Infinix Smart 8, Vivo Y02). | Order flow under 90s end-to-end. List screens under 2s on cached data.
FS-08 | Network handoff WiFi↔SIM | Distributor walking out of shop | Mid-action, walk past WiFi range. | Ongoing request retries / completes; no orphan state.
FS-09 | Battery drain over a real shift | Driver, 4 hours | Start at 100% with location ON. | End ≥60%. If <60%, throttle location ping rate.
FS-10 | Dead-zone tolerance | Driver in a known signal black spot | Place actions inside black spot. | App queues or shows offline; recovers on signal return.
FS-11 | OTP delivery perception | Real distributor in pilot | Watch them log in 5 times across a week. | All complete <60s from Send to Verify. Frustration index logged.
FS-12 | Confused-user think-aloud | Brand-new distributor | Ask them to place an order with no help. | Time + count of 'stuck moments'. >2 stuck moments → UI issue → backlog.
FS-13 | Photo upload on weak 3G | Driver in rural area | Try proof photo at 3G. | Upload completes <60s or queues for retry. App stays usable.
FS-14 | Multiple drivers on live map | Run 3 driver devices concurrently | All online, moving. | Admin map shows all 3 markers updating; no lag >5s.
FS-15 | Push notification delivery | Driver phone with app backgrounded | Admin assigns 5 orders over 30 min. | All 5 push notifications received within ≤30s of assignment.

## Build Backlog
Add every code-change idea here as you test. NOTHING triggers a rebuild on its own — we batch them, then do ONE rebuild that covers all of them.
# | Found in TC-ID | Surface | Problem (what user sees) | Proposed change | Native or JS-only? | Status | Notes

## Defect Log
DEF-ID | TC-ID | Severity (P0/P1/P2) | Title | Steps to reproduce | Expected | Actual | Status | Owner | Found | Fixed in | Notes

## Sign-off
Pilot Go-Live Sign-off
Group | Cases Pass | Cases Fail | Cases Blocked | % Pass | Tester / Date / Comment
A — Cold-Start + Auth (admin + mobile)
B — Distributor — Add Client + Address Search
C — Distributor — Place Order (matrix)
D — Distributor — History, Track, Ledger, Inventory
E — Admin Web — Operations & Order Lifecycle
F — Admin Web — Master Data CRUD
G — Driver — Receive, Scan, Deliver, Return
H — Network Resilience
I — Security & Permissions
J — FIELD — Driver Day-in-the-Life
K — FIELD — Distributor Operations
L — Multi-Day Soak + OTA
Pilot approved for real users:
Approver name
Approver signature
Date